# Open Issues and Development Estimates

LUPMIS2  ·  meeting handout  ·  18 September 2026

Estimates are developer days for one developer, including testing, and exclude time spent waiting on other teams. They are planning figures, not commitments.

## Ready to do now

| Issue | Estimate |
| --- | --- |
| Deploy Service Worker v25 — push the pending commits and status report, deploy, and confirm on one device that stored map tiles survive the update | 0.5 day |
| CARTO key on the deployment build — add the key to the server build configuration; record who holds the CARTO account | 1 hour + admin |
| Thunderforest key — move it out of the source code into configuration, like the CARTO key | 1 hour |
| Radius adjuster on phones — test +/− target size and label position on an iPhone once the remote server is back; fix what turns up | 0.5–1.5 days |
| Typed entry for the Area tool — agree the design first (two fields and a derived total), then build it with the same latitude correction as the circle | 2–3 days |
| API token compiled into the client — move it behind a server-side session so it is no longer visible to users | 2–4 days |
| Digital Earth Africa extract — run it for the pilot district — the first end-to-end test of the raster path | 1–2 days |
| User manual Part 2 — drawing and digitising tools, once the toolbar has had a settled period in the field | 3–4 days |

Subtotal: about 10–16 days

## Waiting on other teams

| Issue (owner) | App work once delivered |
| --- | --- |
| GPS trail endpoint (database team) — outstanding since May | 1–2 days |
| Staged-upload and import-status endpoints (database team) — app side of the upload workflow | 3–5 days |
| Duplicate parcel number policy (database team) — a decision is needed on the upload staging table | 0.5 day |
| Supervisor review interface (database team) — for staged uploads; separate estimate needed if built inside the app | none |
| OpenStreetMap re-import and external-layers tables (database team) — run from the runbook | 1 day |
| Revoke old MinIO storage keys (infrastructure team) — urgent — the old keys stay valid until this is done | none |

Subtotal once delivered: about 5–9 days

## No development needed

Field communication. Officers who work offline should download their areas again after updating to v25; earlier updates removed their stored map tiles.

Schema findings. Four points for the database team, listed in section 3 of the schema summary.

## Not yet built from the Functional Specifications

Checked against LUPMIS2 Functional Specifications v4 (July 2025); section numbers refer to that document. Order-of-magnitude figures for scoping, not plans. Items marked “LUSPA input” cannot be estimated firmly until LUSPA supplies what the TWG notes in the specification ask for.

| Map application gaps | Estimate |
| --- | --- |
| Map layouts and printing (§6) — legend, scale bar, north arrow and title on a print layout; large-format output; export to PNG, SVG and GeoTIFF | 6–10 days |
| Template reports and batch printing (§6) — land use reports, zoning summaries, planning comments — LUSPA input: report templates | 5–8 days |
| Thematic mapping (§2) — custom symbology for zoning, land use and infrastructure | 4–6 days |
| Attribute table (§4) — view, edit, filter and join attribute data | 5–8 days |
| Statistics and pivot tables (§2, §4) — median, mode, variance, standard deviation; field summaries and pivots — LUSPA input | 4–7 days |
| GeoPackage and DXF (§4) — import and export | 5–8 days |
| Topology management (§4) — detect and prevent parcel overlaps, gaps and slivers | 4–6 days |
| Georeferencing (§4) — place scanned plans on the map by control points | 8–12 days |
| Photos in field data collection (§7) — attach photos to locations and features | 3–5 days |
| Site plan during inspection (§1) — show the submitted site plan over the local plan in the field | 3–5 days |
| Local and structure plan amendment (§2) — save drawn changes to plan layers as proposals for review | 5–8 days |
| Role-based access control (§8) — permissions per role in the app and API | 5–8 days |
| Server audit trail (§8) — who changed which data, and when — with the database team | 3–5 days |
| Publish LUPMIS data as WMS/WFS (§5) — with the infrastructure team | 3–5 days |
| Metadata management (§5) — source, date and accuracy recorded per dataset | 3–5 days |
| Cross-browser test pass (§7) — Chrome, Edge, Firefox, Safari; fix findings | 2–3 days |

Subtotal: about 70–110 days

| Larger modules | Estimate |
| --- | --- |
| Raster handling, Stage 2 (§3) — GeoTIFF import/export; resample, reclassify, mosaic; slope, aspect, hillshade. JPEG2000 and ECW need server-side conversion | 15–25 days |
| Street naming, property addressing, UPN assignment (§10) — per Act 925 and LI 2384 — LUSPA input: the procedure | 15–25 days |
| Automated zoning compliance (§1) — check a site plan against setbacks, floor area ratio, heights — needs the zoning table | 8–12 days |
| 3D visualisation (§2) — terrain and building models | 10–15 days |
| Automated local plans (§1, §4) — parcel layout from land use shares — TWG: future consideration | 10–20 days |
| Global datasets and AI (§2) — ERA5, WorldPop, Google Earth Engine — LUSPA input: the definite list | after the list |

Subtotal: about 60–100 days, plus global datasets

## Permitting system (outside the map application)

To be estimated with whoever builds the permitting system: mobile-friendly permit forms (§7); status notifications by email and SMS (§1); fee calculation and payment through Ghana.Gov and GhIPSS, including sale of data under L.I. 2481 (§1); building code validation and evidence validation through other agencies’ APIs (§1); stakeholder and public engagement (§1); and the district procedures in §10 — change of use, rezoning, subdivision, enforcement notices, certificates, and forms 55, 36 and 40.

## Infrastructure, no application development

On-premise deployment and automated backups with tested recovery (§8); access for other departments (§8); and Python or Jupyter access for analysts (§5), which needs a read-only database account rather than application work.