## Work Breakdown
Seq | ID | Workstream | Task | Spec § | Owner | Days (min) | Days (max) | Priority | Source | Notes and dependencies
1 | A4 | Defects & technical debt | Restore .htaccess handling in the PWA container | §8 | Infrastructure | 0.5 | 1 | High | REV | AllowOverride None on /var/www/html: SPA fallback, /embed clean URL and the index.html rewrite are all inert
2 | A6 | Defects & technical debt | Turn off display_errors on the API | §8 | API team | 0.5 | 0.5 | High | REV | Anonymous callers receive PDO stack traces naming tables and constraints
3 | B3 | Security & access | Revoke the old MinIO storage keys | §8 | Infrastructure | 0 | 0 | High | OI | Urgent — the old keys stay valid until revoked. No application work
4 | B2 | Security & access | Rotate the shared API token and revoke the old one | §8 | Infrastructure | 0.5 | 0.5 | High | REV | In committed source since the first commit, and present in the stale bundles under A5
5 | B4 | Security & access | Move the Thunderforest key into configuration | §8 | GIS tools | 0.25 | 0.25 | Low | OI | Still in source; same treatment as the Carto key
6 | B5 | Security & access | Confirm Carto key custody and build-time injection | §8 | GIS tools | 0.25 | 0.25 | Low | OI | Record who holds the Carto account
7 | A5 | Defects & technical debt | Deployment hygiene — prune stale asset chunks | §8 | Infrastructure | 0.5 | 0.5 | Medium | REV | ~95 chunks back to March are still publicly served; deploy does not delete
8 | G1 | Cross-module integration | Parcel-map embed endpoint for the Applicant Portal | §1 | GIS tools | 1 | 2 | High | REV | The Portal team's only outstanding dependency on this module; the portal has no map today
9 | C3 | Database & sync | Duplicate parcel number policy | §4 | Database team | 0.5 | 0.5 | Medium | OI | A decision is needed on the upload staging table before C2 can finish
10 | H4 | Management & infrastructure | LUSPA input — street naming and addressing procedure | §10 | LUSPA | 0 | 0 | High | OI | Blocks E2
11 | H2 | Management & infrastructure | LUSPA input — report templates | §6 | LUSPA | 0 | 0 | Medium | OI | Required before D2 can be estimated firmly
12 | H3 | Management & infrastructure | LUSPA input — statistics and pivot requirements | §2 | LUSPA | 0 | 0 | Medium | OI | Required for D5
13 | H5 | Management & infrastructure | LUSPA input — definitive global dataset list | §2 | LUSPA | 0 | 0 | Low | OI | Blocks E6
14 | H1 | Management & infrastructure | MoU process with the nine stakeholder organisations | §5 | LUSPA / project | 0 | 0 | High | SR9 | Begin with ECG and Civil Aviation. Blocks data integrations, not code
15 | C6 | Database & sync | Index spatial.lu_parcels | §4 | Database team | 1 | 2 | High | REV | 3.1 million rows with zero indexes — every query is a sequential scan
16 | C7 | Database & sync | Declare the parcel geometry column properly | §4 | Database team | 0.5 | 1 | Medium | REV | Column is bare 'geometry', so catalogues report SRID 0 while the data is EPSG:4326
17 | C8 | Database & sync | Migrate collector-zone WKT text to a geometry column | §4 | Database team | 1 | 2 | Medium | REV | Zone boundaries are WKT in a text column; unusable to PostGIS until cast, then needs a GiST index
18 | A1 | Defects & technical debt | Wire the Save action in the drawing toolbar | §4 | GIS tools | 1 | 2 | High | REV | onEditEvent('save') is defined but no listener is registered, so edits are never written back
19 | B1 | Security & access | Move the API token behind a server-side session | §8 | GIS tools | 2 | 4 | High | OI | Token is compiled into the client bundle and readable by any user
20 | B6 | Security & access | Role-based access control in the app and API | §8 | GIS tools | 5 | 8 | High | OI | Landing-page module access is already live on the permitting side; the app and API are not
21 | B7 | Security & access | Server-side audit trail | §8 | GIS tools + DB | 3 | 5 | Medium | OI | Who changed which data, and when. Client-side event log is complete
22 | C9 | Database & sync | Data validation rules for parcels and locations | §4 | GIS tools + DB | 2 | 4 | Medium | SR9 | Recommended in section 10 to assure data quality from the field
23 | A3 | Defects & technical debt | Fix zone labelling in zonal statistics | §2 | GIS tools | 1 | 2 | Medium | REV | Labels come from the first matching field, which is not unique — repeated zone names observed
24 | A2 | Defects & technical debt | Move overlay and zonal analysis off the main thread | §2 | GIS tools | 3 | 5 | High | REV | Measured: ~9 s frozen map at 8 000 features. Needs a Web Worker
25 | D6 | Map application gaps | GeoPackage and DXF import and export | §4 | GIS tools | 5 | 8 | High | OI | DXF was raised directly in the pilot district workshops
26 | D9 | Map application gaps | Photographs in field data collection | §7 | GIS tools | 3 | 5 | High | OI | Attach photographs to locations and features; also in Status Report v9 section 10
27 | A7 | Defects & technical debt | Radius adjuster on phones | §7 | GIS tools | 0.5 | 1.5 | Medium | OI | Target size and label position; test on a physical iPhone
28 | A8 | Defects & technical debt | Typed coordinate entry for the Area tool | §2 | GIS tools | 2 | 3 | Medium | OI | Agree the design first — two fields and a derived total — then build with the latitude correction
29 | D3 | Map application gaps | Thematic mapping | §2 | GIS tools | 4 | 6 | High | OI | Custom symbology for zoning, land use and infrastructure
30 | D1 | Map application gaps | Map layouts and printing | §6 | GIS tools | 6 | 10 | High | OI | Legend, scale bar, north arrow, title; large format; PNG, SVG and GeoTIFF output
31 | D4 | Map application gaps | Attribute table | §4 | GIS tools | 5 | 8 | High | OI | View, edit, filter and join attribute data
32 | C2 | Database & sync | Staged upload and import-status endpoints — application side | §4 | GIS tools | 3 | 5 | High | OI | Blocked on the database team
33 | C1 | Database & sync | GPS trail endpoint — application side | §7 | GIS tools | 1 | 2 | Medium | OI | Blocked: endpoint outstanding from the database team since May
34 | C4 | Database & sync | Supervisor review interface for staged uploads | §4 | Database team | 0 | 0 | Medium | OI | Separate estimate required if it is built inside the map application
35 | C5 | Database & sync | OpenStreetMap re-import and external-layer tables | §5 | Database team | 1 | 1 | Low | OI | Run from the existing runbook
36 | D14 | Map application gaps | Cross-browser test pass | §7 | GIS tools | 2 | 3 | Medium | OI | Chrome, Edge, Firefox and Safari, then fix what is found
37 | F1 | Documentation & training | User Manual Part 2 — drawing and digitising | — | GIS tools | 3 | 4 | Medium | OI | Once the rebuilt toolbar has had a settled period in the field
38 | F2 | Documentation & training | Training Topics 11 and 12 | — | GIS tools | 4 | 6 | Medium | REV | The last two workbooks of the twelve-topic handover programme; Topics 0–10 are delivered
39 | D2 | Map application gaps | Template reports and batch printing | §6 | GIS tools | 5 | 8 | Medium | OI | Land use reports, zoning summaries, planning comments. Needs LUSPA templates (H2)
40 | D5 | Map application gaps | Statistics and pivot tables | §2, §4 | GIS tools | 4 | 7 | Medium | OI | Median, mode, variance, standard deviation; field summaries and pivots. Needs LUSPA input (H3)
41 | D7 | Map application gaps | Topology management | §4 | GIS tools | 4 | 6 | Medium | OI | Detect and prevent parcel overlaps, gaps and slivers
42 | D10 | Map application gaps | Site plan display during inspection | §1 | GIS tools | 3 | 5 | Medium | OI | Show the submitted site plan over the local plan in the field
43 | D11 | Map application gaps | Local and structure plan amendment | §2 | GIS tools | 5 | 8 | Medium | OI | Save drawn changes to plan layers as proposals for review
44 | D12 | Map application gaps | Publish LUPMIS data as WMS/WFS | §5 | GIS tools + infra | 3 | 5 | Medium | OI | Outbound services for other agencies
45 | D13 | Map application gaps | Metadata management | §5 | GIS tools | 3 | 5 | Low | OI | Source, date and accuracy recorded per dataset
46 | D8 | Map application gaps | Georeferencing of scanned plans | §4 | GIS tools | 8 | 12 | Medium | OI | Place scanned plans on the map by control points
47 | G2 | Cross-module integration | Hand generated parcels from the Parcel Generator into the GIS tools | §4 | GIS tools | 3 | 5 | Medium | REV | Parcel team reports the generator working; the handover for editing is not built
48 | E7 | Larger modules | Digital Earth Africa extract for the pilot district | §3 | GIS tools | 1 | 2 | Medium | OI | First end-to-end test of the raster path; precursor to E1
49 | E3 | Larger modules | Automated zoning compliance | §1 | GIS tools | 8 | 12 | High | OI | Setbacks, floor area ratio and heights against a site plan; needs the zoning table
50 | E2 | Larger modules | Street naming, property addressing and UPN assignment | §10 | GIS tools | 15 | 25 | High | OI | Per Act 925 and LI 2384. Blocked on the LUSPA procedure (H4)
51 | E1 | Larger modules | Raster handling, Stage 2 | §3 | GIS tools | 15 | 25 | Medium | OI | GeoTIFF import/export; resample, reclassify, mosaic; slope, aspect, hillshade. JPEG2000 and ECW need server-side conversion
52 | F3 | Documentation & training | Video tutorials for field staff | — | GIS tools | 3 | 5 | Low | SR9 | Requested by workshop participants; recommended in section 10
53 | H6 | Management & infrastructure | On-premise deployment and automated backups with tested recovery | §8 | Infrastructure | 0 | 0 | High | OI | No application development
54 | H7 | Management & infrastructure | Access for other departments | §8 | Infrastructure | 0 | 0 | Medium | OI | No application development
55 | H8 | Management & infrastructure | Read-only database account for Python/Jupyter analysts | §5 | Infrastructure | 0 | 0 | Low | OI | No application development
56 | E5 | Larger modules | Automated local plans | §1, §4 | GIS tools | 10 | 20 | Low | OI | Parcel layout from land use shares. TWG marked it a future consideration
57 | E4 | Larger modules | 3D visualisation | §2 | GIS tools | 10 | 15 | Low | OI | Terrain and building models. Deferred: conflicts with the offline-first design
58 | E6 | Larger modules | Global datasets and AI | §2 | GIS tools | 0 | 0 | Low | OI | ERA5, WorldPop, Earth Engine. Cannot be estimated until LUSPA supplies the list (H5). ECMWF open data was assessed and rejected as too coarse
59 | G3 | Cross-module integration | Permit status notifications by email and SMS | §1 | Permitting team | 0 | 0 | High | OI | To be estimated by whoever builds the permitting system
60 | G4 | Cross-module integration | Fee calculation and payment | §1 | Permitting team | 0 | 0 | High | OI | GhanaDotGov selected as provider; its payment API is under development
61 | G5 | Cross-module integration | Mobile-friendly permit forms | §7 | Permitting team | 0 | 0 | Medium | OI | To be estimated by whoever builds the permitting system

## Summary
Workstream | Tasks | Days (min) | Days (max) | Of which blocked or not estimable
Defects & technical debt | 8 | 9 | 15.5 | 0
Security & access | 7 | 11 | 18 | 1
Cross-module integration | 5 | 4 | 7 | 3
Database & sync | 9 | 10 | 17.5 | 1
Management & infrastructure | 8 | 0 | 0 | 8
Map application gaps | 14 | 60 | 96 | 0
Documentation & training | 3 | 10 | 15 | 0
Larger modules | 7 | 59 | 99 | 1
TOTAL — estimated development | 61 | 163 | 268 | 14
Reading these figures
Developer days for one developer, including testing. They are planning figures, not commitments.
Zero means no application development is required, or the item cannot be estimated until an input arrives — see the Notes column.
Time spent waiting on other teams is excluded; items blocked on them are marked in Owner and Notes.
Source: OI = Open Issues and Estimates, 18 September 2026 · SR9 = Development Status Report v9, section 10 · REV = found during the October 2026 review of the running system.
Items closed since the September handout are listed on the third sheet, so nothing appears twice.
Sequence — the Seq column is a recommended start order, not a claim that the work is serial. Tasks with different owners run in parallel.
Seq 1-14 — unblock what is already built, and raise every long-lead request now. A4 comes first because it leaves the deployed session fix inert; the LUSPA inputs and the MoU process are started here only because they have the longest lead times.
Seq 15-24 — foundations. Index and repair the parcel and zone data before features are built on it, wire the Save action, and put access control and the audit trail in place.
Seq 25-38 — the pilot-workshop feedback and the specification gaps closest to daily use, plus the upload workflow once the database team's endpoints arrive.
Seq 39-61 — the remaining specification scope, ending with the items owned by the permitting team and those deferred by the TWG.

## Closed since 18 Sep
Item | Was listed in | Outcome
Deploy Service Worker v25 | OI 18 Sep | Done — v29 deployed 13 Oct 2026; tile cache pinned at v24 so stored tiles survive updates
Offline database never opened in production | — | Done — v27: the worker script was being skipped by the service worker
Drawing rail option bar covered the Transform button | — | Done — v27, an ol-ext CSS specificity defect
Module renamed to GIS Tools | — | Done — v28, across the app, manifest and installed icon
No session injected on the landing-page link | — | Code done — v29 routes /index.html through index.php, but it is inert until A4 is fixed
API base hostname compiled into the bundle | — | Done — now the same-origin relative path /api; zero hostnames in the build
SSO validation called the public hostname from inside the server | — | Done — now http://l4lmainbackend/sso/validate; removed a 30 s stall on sign-in
Training Topics 0 to 10 | — | Delivered — eleven workbooks, about 110 hours
ECMWF open data assessment | — | Closed — assessed and rejected; the forecast grid is far too coarse for parcel-level work
Payment provider selection | OI 18 Sep | Closed — GhanaDotGov (ghana.gov) selected; its API is in development (see G4)